## Slide 1
Notes: This presentation organizes the current plan into a sequence for discussion. Each section can be expanded, reduced or reassigned as decisions are made.

## Slide 2
INTRODUCTION
Purpose of the Dallas production plan
02
WHY THIS EXISTS
This proposal covers Dallas only. No other cities or continuing commitments are assumed. The plan brings the program, proposed funding and production work together for Freedom House review and permission to begin outreach.
PLANNING QUESTIONS
Does the sequence reflect how Freedom House makes decisions?
Who needs to participate in each approval?
What belongs in the first financing round?
Explain the current plan
Identify decisions and dependencies
Track staffing, financing and delivery
WORKING DRAFT
AMERICA TOGETHER
Notes: The deck should remain useful after an initial presentation. It serves as a living planning document, with concise narrative on the slide and detailed discussion in the speaker notes.

## Slide 3
FOUNDATION
Current position
03
WHAT IS ALREADY IN PLACE
The program story, four-day structure, Freedom House purpose and preliminary Dallas financial model have been developed. The next work converts the concept into an approved, financed and staffed operating plan.
PLANNING QUESTIONS
Which elements already have final approval?
Which assumptions still require validation?
What must be complete before outside outreach begins?
Final America Together program description
Executive summary and Dallas working budget
The American Table identity and program narrative
Preliminary sponsorship structure
WORKING DRAFT
AMERICA TOGETHER
Notes: The working Dallas budget totals $1,653,300, with a minimum funding target of $1,750,000. The staffing model and first year operating capital now require a separate review.

## Slide 4
ROADMAP
Development path
04
The project moves through five decision periods.
SEPTEMBER
Plan and budget
OCTOBER 1
Outreach approval
NOVEMBER
Freedom House
Formal Approval
MARCH 1
Dallas presentation
AFTER DALLAS
Final report
Working targets only. Approval, funding and availability govern commitments.
WORKING DRAFT
AMERICA TOGETHER
Notes: The dates create a working cadence. October 1 is the central approval point. March 1 tests the Dallas model. The May or June presentation demonstrates whether America Together can become a continuing national platform.

## Slide 5
PREPARATION
September 18 delivery
05
MATERIALS DELIVERED FOR REVIEW
Laura and Brad deliver the sponsor invitation and production plan by September 18. The materials set out the program, proposed funding and next steps. Actual production costs require quotes. Permission to begin outreach is the next decision.
PLANNING QUESTIONS
Which venue assumptions require estimates?
What is needed to authorize outreach?
Preliminary Dallas financial assumptions
Dallas contract production budget
Proposed program and working schedule
Freedom House board briefing materials
Participant and sponsor briefing materials
WORKING DRAFT
AMERICA TOGETHER
Notes: This period should also identify legal and ownership requirements associated with any proposed HAP collection sale. Preliminary venue holds may proceed where they do not create an unauthorized commitment.

## Slide 6
DECISION
Permission to begin funding outreach
06
GREEN LIGHT BEFORE OUTREACH
Seek written permission to use the sponsor invitation and Freedom House name in coordinated funding discussions. Agree on an outreach contact, who receives funds and who signs contracts. Final event approval and spending commitments require separate decisions.
PLANNING QUESTIONS
What does the early authority permit?
What cash releases the first contracts?
Who signs contracts and receives funds?
What HAP sale authority is granted?
Contract producer scope and seed budget
Venue and production estimates after approval
Speaker and music inquiries after approval
Presenting sponsor approach after approval
HAP sale planning and authority are defined
WORKING DRAFT
AMERICA TOGETHER
Notes: No outside communication should imply that a public figure, sponsor, venue or Freedom House has committed until the relevant party has confirmed participation in writing.

## Slide 7
ORGANIZATION
Contracted production model
07
Laura and Brad guide development. A contracted executive producer coordinates Dallas through defined scopes, agreed fees and specialist vendors.
DALLAS CONTRACT LEADERSHIP
Leadership and general management
Development and sponsorship
Production leadership
Marketing and communications
Finance and administration
Program and Freedom House content
SHOW SPECIFIC TEAM
Technical crews and stage management
Security and medical personnel
Hospitality and guest services
Art handlers and installers
Drivers, runners and temporary assistants
Venue and production vendors
WORKING DRAFT
AMERICA TOGETHER
Notes: Annual employment should remain subject to available funding and the success of the first presentation. Employment counsel should prepare the final agreements. Temporary labor and vendor costs remain in the Dallas event budget.

## Slide 8
ORGANIZATION
First production contracts
08
AFTER APPROVAL AND INITIAL FUNDING
The first contracts establish production estimates, sponsorship support and financial control. Start with a defined development assignment and release further work as funding becomes available.
PLANNING QUESTIONS
Which role has daily authority?
Founder and Executive Producer
Contracted Executive Producer
Development and Sponsorship Director
Production Director
Finance and Administration Manager
WORKING DRAFT
AMERICA TOGETHER
Notes: The annual salary model should be presented as the creation of a continuing organization. The first financing round must cover the team through Dallas and the decision period that follows.

## Slide 9
ORGANIZATION
Specialist production support
09
AS SCOPE AND FUNDING REQUIRE
Specialist contractors prepare the program, communications and delivery. The producer defines each assignment, fee and approval process within the funded Dallas scope.
PLANNING QUESTIONS
Which functions require dedicated support?
Which advisers should remain independent?
Who manages public communications?
Who coordinates Freedom House approvals?
Marketing and Communications Director
Program and Freedom House Content Director
Project Coordinator
Public relations support
Legal, insurance and accounting advisers
Ticketing and audience development support
WORKING DRAFT
AMERICA TOGETHER
Notes: Legal, insurance, accounting and specialized public relations work may be more appropriate as professional service engagements. The staffing budget should separate salaries, benefits, retainers and show specific fees.

## Slide 10
RELATIONSHIPS
Major participant outreach
10
OUTREACH AFTER APPROVAL
After outreach approval, explore the proposed conversation with President George W. Bush, President Barack Obama and Ken Burns. In parallel, approach the other conversation participants. Establish interest, date options, requirements and costs. All names remain proposed.
PLANNING QUESTIONS
What role are we asking each person to play?
What date and venue information can we provide?
What remains confidential?
Prepare individual briefings and several date options
Coordinate all approaches with Freedom House
Track availability without implying commitment
Define essential participants and alternative formats
WORKING DRAFT
AMERICA TOGETHER
Notes: The names on this slide identify prospective outreach only. They do not represent confirmed participation. The final deck for external circulation may omit this slide until the outreach strategy is approved.

## Slide 11
FINANCING
Sponsorship development
11
INTRODUCTIONS BEGIN WITH APPROVAL
After written outreach permission, use the invitation to pursue $4.8 million or more in proposed support. Seek a $600,000 presenting sponsor with an initial payment for approved development and deposits. Coordinate every approach with Freedom House.
PLANNING QUESTIONS
Which sponsors receive the first meetings?
What rights accompany each level?
What initial payment funds development?
Presenting Sponsor
Freedom and Democracy Sponsor
Arts and Culture Sponsor
Civic Dialogue Sponsor
Music and Performance Sponsor
The American Table underwriting
WORKING DRAFT
AMERICA TOGETHER
Notes: The current working model provides sponsorship capacity of $3,000,000 or more. Final pricing and benefits require legal, accounting and market review before circulation.

## Slide 12
FORMAL APPROVAL
November formal Freedom House approval
12
WHAT MUST BE READY
The Sea Island Board of Directors meeting is the target for formal Freedom House approval. Communications, media, social media, ticketing promotion, sponsor publicity, and public use of participant names remain private until all readiness conditions are met and release clearance is given.
PLANNING QUESTIONS
What does the board formally approve?
What conditions remain before release?
Who gives final communications clearance?
When may ticket sales and publicity begin?
Approved program, mission narrative, and relationship
Confirmed governance, authority, and financing plan
Private communications and media readiness
Confidential sponsor and participant status
Ticketing, audience, and release controls
Approved HAP sale authority and process
WORKING DRAFT
AMERICA TOGETHER
Notes: November is the target for formal Freedom House approval at the Sea Island Board meeting. It is not a public announcement date. Public communications begin only after approval, financing, contracts, participants, venue, production, media, ticketing, and release authority are ready.

## Slide 13
DELIVERY
Production period
13
December through February converts the approved plan into a complete Dallas presentation.
DECEMBER
Venues, vendors, principal sponsors and program structure
JANUARY
Participants, ticketing, travel, hospitality and local media
FEBRUARY
Final sales, security, rehearsals and operational readiness
PLANNING QUESTIONS
Which commitments are on the critical path?
What must be contracted by December?
What is the final cancellation point?
WORKING DRAFT
AMERICA TOGETHER
Notes: A detailed production schedule will eventually sit beneath this summary. The planning version should track owners, deadlines, dependencies, approved costs and actual costs.

## Slide 14
FIRST PROGRAM
March 1 Dallas presentation
14
DALLAS PROGRAM DELIVERY
Dallas brings the four program experiences together to support Freedom House, engage sponsors and audiences, and demonstrate the quality and financial outcome of this event.
PLANNING QUESTIONS
What defines success?
What financial result must the program achieve?
What evidence will sponsors and the board receive?
When does the team decide to proceed?
Program delivery and audience experience
Freedom House storytelling and mission impact
Sponsorship and ticket performance
Press, digital engagement and audience growth
Operational performance and safety
WORKING DRAFT
AMERICA TOGETHER
Notes: The detailed four day schedule remains in the master plan. This slide focuses on the business and organizational purpose of the first presentation.

## Slide 15
DALLAS CLOSEOUT
Dallas closeout and final report
15
AFTER THE DALLAS EVENT
The team reconciles Dallas revenue and expenses, completes supplier obligations and reports the program and fundraising results to Freedom House and sponsors. The governing agreement determines the final beneficiary payment.
PLANNING QUESTIONS
Who approves the final Dallas accounts?
Which supplier obligations remain?
Have all sponsor benefits been delivered?
When is the beneficiary payment due?
Reconcile revenue and expenses
Report results to Freedom House and sponsors
Document audience and media response
Settle outstanding costs and obligations
Complete the beneficiary payment and final report
WORKING DRAFT
AMERICA TOGETHER
Notes: The second presentation is targeted for May or June. The date must remain flexible until Dallas funding, venue availability and production capacity are confirmed.

## Slide 16
NEXT DISCUSSION
Dallas development funding
16
The first funding must cover approved development and deposits before larger commitments.
USES OF FUNDS
Contracted producer and development support
Dallas program expenses
Professional services and insurance
Venue and talent deposits within approved scope
Working capital and contingency
DECISIONS TO MAKE NEXT
Contract scopes and quoted fees
Contract sequence and payment triggers
Dallas cost allocation
HAP sale proceeds and restrictions
Minimum cash before the first commitments
DISCUSSION DRAFT
AMERICA TOGETHER
Notes: The next step is a position by position staffing model with salary, start date, employment cost, reporting line and funding source. That schedule will show the cash required at approval and through the March review period.

## Slide 17
PERSONNEL
Production personnel planning
17
WORKING DRAFT
AMERICA TOGETHER
Dallas contracts cover development, delivery and closeout within the approved event budget.
DALLAS AUTHORIZATION
Founder preparation begins September 1, 2026
October 1 operating target requires approval and cash
Working Dallas presentation date is March 1, 2027
DALLAS CONTRACT CONTROLS
Each agreement defines its Dallas scope and fee
Approved funding must support every commitment
The producer tracks payments and closeout obligations
Contract leadership and specialist vendors report through the agreed Dallas production structure.
Notes: Use this slide to explain the two stage commitment. Dallas contracts may state future pricing, but they do not create an automatic national obligation.

## Slide 18
LEADERSHIP
Founder and production company structure
18
WORKING DRAFT
AMERICA TOGETHER
ROLE OR AGREEMENT
WORKING STRUCTURE
Brad Hillinger
Co Founder and Executive Producer
Laura Roosevelt
Co Founder
Roose Hill LLC
Producer and production company banner
Dallas production fee
$150,000 proposed fixed fee
Contract scope
Dallas development, event delivery and closeout
A Dallas agreement must define scope, payment terms, travel, reimbursable costs and the responsibilities of Roose Hill LLC and the contracted Lead Producer.
Notes: Laura Roosevelt remains Co Founder without an assigned operating position. Roose Hill is spelled with two o letters.

## Slide 19
SCHEDULE
Proposed Dallas contract schedule
19
WORKING DRAFT
AMERICA TOGETHER
SEP 1
Brad Hillinger and Laura Roosevelt
Founder preparation
OCT 1
Lead Producer, Development Director, Finance Manager
Operating authority and funding control
OCT 7
Project Coordinator
One schedule and planning record
OCT 15
Art, Music, Food, and Kitchen Table Directors
The four program leaders begin
NOV 1
Marketing Director and Freedom House Content Director
Private communications preparation and approved content
Working dates depend on approval, cash and availability. Contract terms must cover delivery and closeout.
Notes: These are the proposed start dates for recruiting and budgeting. Offers remain subject to Freedom House approval, financing, and signed agreements.

## Slide 20
COSTS
Dallas contract fee allowances
20
WORKING DRAFT
AMERICA TOGETHER
POSITION
START
PLANNING FIGURE
Lead Producer
Oct 1
$95,000
Development and Sponsorship Director
Oct 1
$70,000
Finance and Administration Manager
Oct 1
$55,000
Project Coordinator
Oct 7
$45,000
Art Director
Oct 15
$65,000
Music Director
Oct 15
$60,000
Food Director
Oct 15
$60,000
Kitchen Table Director
Oct 15
$60,000
Marketing and Communications Director
Nov 1
$60,000
Freedom House Content Director
Nov 1
$50,000 allowance
Planning allowances require scopes and supplier quotes. Use contracted services. Confirm travel, expenses and included vendor personnel costs before commitments.
Notes: Compensation figures are working estimates, not offers. Benchmarks include the U.S. Bureau of Labor Statistics 2025 wage data for producers, event planners, art directors, fundraising and public relations managers, and financial managers: https://www.bls.gov/ooh/

## Slide 21
PROGRAM TEAM
Four directors build one public experience
21
WORKING DRAFT
AMERICA TOGETHER
ART DIRECTOR
$65,000 Dallas
Art program, lenders, installation, security, and transfer plan
MUSIC DIRECTOR
$60,000 Dallas
Artists, repertoire, rights, rehearsals and Dallas production
FOOD DIRECTOR
$60,000 Dallas
The American Table, chefs, menu, service, hospitality, and city partners
KITCHEN TABLE DIRECTOR
$60,000 Dallas
Day Four design, participants, facilitators, briefing, and documented outcomes
Each director reports to the Lead Producer under a Dallas project agreement. Start dates depend on approval and funding. Scope and fees require confirmation.
Notes: The four directors form the program production team. They begin in Dallas and should be selected for the ability to build a repeatable national model.

## Slide 22
PRODUCTION
Dallas contract personnel and firms
22
WORKING DRAFT
AMERICA TOGETHER
CONTRACT PRODUCTION PERSONNEL
Production Manager and Technical Director
Venue and Site Manager and Stage Managers
Participant, Hospitality, and Travel Managers
Ticketing, Audience, and Volunteer Managers
Security, medical, art installation, and retail leads
OUTSIDE FIRMS
Legal, accounting, payroll, insurance, and risk
Public relations, website, digital, and ticketing platform
Technical production, security, and medical services
Catering, transportation, printing, signage, and merchandise
The Lead Producer should issue the Dallas staffing and procurement schedule by October 31, 2026. Every commitment requires a written scope, price, approval authority, and budget source.
Notes: These positions and firms enter as the Dallas venue, production plan, and budget become final. Future cities receive new local budgets and do not inherit Dallas prices automatically.

## Slide 23
PLANNING CALENDAR
Schedule of activities
23
WORKING DRAFT
AMERICA TOGETHER
DATE
ACTIVITY AND DECISION
SEP 1 to SEP 30
Founder preparation, sponsor invitation, contract budget and candidates. Outreach awaits permission.
OCT 1
Target for authorized development, subject to initial cash and signed scopes
OCT 7 to OCT 31
Subject to approval: parallel speaker, music, sponsor and venue discussions with contracted production support
NOVEMBER
Formal Freedom House approval at the Sea Island Board of Directors meeting; communications remain private until release clearance
DECEMBER
Venue, vendors, principal sponsors, program structure, contracts, and insurance
JANUARY
Participants, ticketing, travel, hospitality, local media, and production detail
FEBRUARY
Final sales, security, rehearsals, installation, run of show, and operational readiness
MARCH 1
Dallas presentation
MARCH 2 to APRIL 15
Financial and program closeout, sponsor report, team review and beneficiary payment
FINAL REPORT
Final Dallas accounts and Freedom House benefit, with outstanding obligations resolved
Working dates for planning. Final dates move only through the approved decision process.
Notes: This schedule should become the working planning calendar. The next revision can break each period into owners, dependencies, due dates, and status.

## Slide 24
FINANCIAL MODEL
Revenue and mission funding model
24
WORKING DRAFT
AMERICA TOGETHER
The funding goal is sponsor coverage of production. Actual costs determine the Freedom House benefit.
DALLAS ATTENDANCE
FINANCIAL PURPOSE
Music
2,000
Kitchen Table Conversations
2,000
HAP and NO WAR
6,000
The American Table
600
Sponsor coverage remains a target pending cash commitments and quotes
Ticket sales are recorded separately from sponsorship revenue
Approved deductions and reserves are settled at city closeout
Remaining proceeds benefit Freedom House under the governing agreement
Planning assumption: ticket revenue may cover production costs that sponsorship does not meet. Settle all costs and obligations before determining the Freedom House benefit.
Notes: The model separates production underwriting from ticket revenue. Final legal, tax, accounting, and charitable language requires Freedom House approval.

## Slide 25
TOP TIER MODEL
Dallas revenue potential
25
WORKING DRAFT
AMERICA TOGETHER
PROGRAM
CAPACITY
GROSS POTENTIAL
Music for America Together
2,000
$2,350,000
The American Table
600
$1,550,000
Kitchen Table Conversations
2,000
$685,000
HAP and NO WAR
6,000
$70,000
Total ticket revenue
10,600
$4,655,000
Presenting Sponsor
One
$600,000
Combined gross potential
$5,255,000
Illustrative $5.255 million gross includes full ticket sales and the lead sponsor only. Additional sponsorship is separate. Costs and name permissions remain to be confirmed.
Notes: Art revenue uses 2,000 admissions at an average of $12.50. Gross potential excludes other sponsorship categories and does not deduct ticketing costs, taxes, refunds, reserves, or production expenses.

## Slide 26
SPONSOR UNDERWRITING
Proposed Dallas sponsorship targets
26
WORKING DRAFT
AMERICA TOGETHER
$4.8 million or more in proposed support. Costs require quotes and funding commitments.
Sponsorship category | Positions | Each | Target
Lead Presenting Sponsor | 1 | $600,000 | $600,000
Freedom and Democracy | 2 | $400,000 | $800,000
Arts and Culture | 1 | $400,000 | $400,000
Civic Dialogue | 2 | $400,000 | $800,000
Music and Performance | 3 | $400,000 | $1,200,000
The American Table | 2 | $300,000 | $600,000
Major donors and contributed support | Multiple | Varies | $400,000+
Total proposed support |  |  | $4,800,000+
Separate cash from donated goods and services. The quoted budget will determine the cash required before commitments.

## Slide 27
FUNDS FLOW
Revenue accounting and Freedom House benefit
27
WORKING DRAFT
AMERICA TOGETHER
01
Sponsor funding
Commit the complete city production budget and working capital.
02
Ticket sales
Record gross sales separately for all four public programs.
03
Approved deductions
Settle all costs, including production gaps, refunds, charges, taxes and reserves.
04
City closeout
Reconcile sponsor coverage, expenses, ticket sales, and outstanding obligations.
05
Freedom House benefit
Transfer remaining net proceeds under the governing agreement.
Gross ticket sales are the starting point. Net proceeds are the amount that benefits Freedom House.
Notes: Ticket purchases may include a purchased benefit and a charitable component. Sponsor acknowledgment and advertising receive different tax treatment. Counsel and accountants must approve the structure and disclosures.

## Slide 28
VENUE PLANNING
Dallas venue candidates and requirements
28
WORKING DRAFT
AMERICA TOGETHER
Music and conversations
SMU McFarlin Auditorium is a candidate. Confirm 2,000 sellable seats after production, security and sponsor holds, plus available date windows.
The American Table
George W. Bush Presidential Center is a candidate for review. Confirm that the approved 600 guest table layout, catering and service requirements can fit.
HAP and NO WAR
Meadows Museum or Dallas Museum of Art are candidates. Confirm exhibition space, installation, security, permissions and attendance across several days.
Venue confirmation
Obtain proposals covering rental, labor, technical services, security, catering and deposits. Confirm layout and capacity directly before selecting a venue.
Candidates carried forward for investigation. No venue or capacity is confirmed.

## Slide 29
VENUE QUALIFICATION
Dallas venue requirements
29
WORKING DRAFT
AMERICA TOGETHER
MUSIC
A primary performance venue must support approximately 2,000 paid seats after security, production, sponsor and participant holds.
KITCHEN TABLE CONVERSATIONS
A 2,000 seat venue must support recording, stage production, accessibility and national participant security.
THE AMERICAN TABLE
A distinctive venue must seat 600 for dinner with practical catering, service aisles, loading, backstage space and guest security.
HAP AND NO WAR
The art installation may use a museum, university gallery or civic site. Its capacity can be smaller because admissions may be timed across several days.
Dallas proceeds when venues, funding, audience demand, security and Freedom House approvals work together.
Notes: These standards make the 8, 10 and 14 city options practical planning choices rather than a promised route. Art capacity differs because the exhibition can use timed admissions over multiple days.

## Slide 30
TICKET SALES MODEL
Ambitious top tier gross sales model
30
WORKING DRAFT
AMERICA TOGETHER
This model assumes permission to use every participant’s name in ticket sales.
PROGRAM
CAPACITY OR ATTENDANCE
GROSS POTENTIAL
Music for America Together
2,000 seats
$2,350,000
The American Table
600 seats
$1,550,000
Kitchen Table Conversations
2,000 seats
$685,000
HAP and NO WAR
6,000 admissions
$70,000
Estimated ticket revenue
$4,655,000
Presenting Sponsor plus ticket revenue
$5,255,000
Notes: This is an ambitious gross sales model, not a guarantee or net income forecast. It assumes permission to use every participant’s name in ticket sales.

## Slide 31
TICKET SALES MODEL
Music for America Together
31
WORKING DRAFT
AMERICA TOGETHER
CAPACITY 2,000
TICKET LEVEL
SEATS
PRICE
GROSS
Founders Circle
100
$5,000
$500,000
Leadership Seating
300
$2,500
$750,000
Premium Orchestra
600
$1,000
$600,000
Reserved Seating
1,000
$500
$500,000
Music total
2,000
$2,350,000
Pricing assumes exceptional talent and strong demand. Confirmed participants and market response must support it.
The $5,000 level must include more than a good seat, such as a private reception or a broader America Together patron package.
Notes: The Founders Circle requires a meaningful access or patron benefit beyond seating. Final benefits, participant names and sales language require approval.

## Slide 32
TICKET SALES MODEL
The American Table
32
WORKING DRAFT
AMERICA TOGETHER
CAPACITY 600
DINNER LEVEL
SEATS
PRICE
GROSS
Founders Table Seating
100
$5,000
$500,000
Leadership Table Seating
200
$3,000
$600,000
Patron Seating
300
$1,500
$450,000
The American Table total
600
$1,550,000
Average dinner price: approximately $2,583 per guest
COMPLETE TABLES OF TEN
Founders Table
$50,000
Leadership Table
$30,000
Patron Table
$15,000
The 60 communal tables remain part of the shared American Table design even when a company, family or donor underwrites an entire table.
Notes: The average price is aggressive but conceivable for a highly limited national program connected to Freedom House and major participants.

## Slide 33
TICKET SALES MODEL
The Kitchen Table Conversations
33
WORKING DRAFT
AMERICA TOGETHER
CAPACITY 2,000
TICKET LEVEL
SEATS
PRICE
GROSS
Leadership Circle
200
$1,000
$200,000
Priority Seating
500
$500
$250,000
Preferred Seating
700
$250
$175,000
General Seating
600
$100
$60,000
Kitchen Table total
2,000
$685,000
The program must offer genuine intellectual and civic value at every ticket level.
Higher levels may include preferred seating, briefing materials, a participant reception or access to another part of the four-day program.
Notes: Premium benefits must remain appropriate to the civic program and must receive participant and Freedom House approval.

## Slide 34
TICKET SALES MODEL
HAP and NO WAR and total gross potential
34
WORKING DRAFT
AMERICA TOGETHER
Art revenue depends on attendance across several days,
not the number of people in the room at one time.
ADMISSION
ATTENDANCE
GROSS
$15 admission
2,000
$30,000
$10 admission
4,000
$40,000
Art total
6,000
$70,000
A strong result of 10,000 visitors at an average of $12 could produce approximately $120,000.
TOP TIER GROSS POTENTIAL
Music for America Together
$2,350,000
The American Table
$1,550,000
Kitchen Table Conversations
$685,000
HAP and NO WAR
$70,000
Estimated ticket revenue
$4,655,000
Presenting Sponsor
$600,000
Combined ticket and sponsor revenue
$5,255,000
Notes: The art base case totals $70,000. The full per city ticket estimate is $4,655,000. Adding the $500,000 Presenting Sponsor gives combined gross potential of $5,155,000.

## Slide 35
NEXT STEPS
Immediate decisions and what comes next
35
WORKING DRAFT
AMERICA TOGETHER
DALLAS OUTREACH APPROVAL REQUEST
01
Permission to proceed
Approve coordinated funding outreach using the invitation and Freedom House name. Confirm the approval contact, fund recipient and contracting authority.
02
Parallel discussions
After permission, explore speakers, music headliners, the presenting sponsor and venues together. A contracted producer develops the cost estimates.
03
Before public release
Secure formal Freedom House approval, participant permissions, financing, contracts, security readiness, ticket controls and communications clearance.
04
Booking decision
Review talent interest, workable dates, venue proposals, quoted costs and initial cash. Decide what can be contracted before confirming Dallas publicly.
Desired outcome
Written outreach permission, named owners and a scheduled review of funding and feasibility.
Notes: The meeting should end with a defined approval path, October 1 seed funding authority or next approval action, named owners, and permission boundaries for confidential outreach. No public announcement begins until the full readiness conditions are met.

## Slide 36
DEVELOPMENT
Speakers, music and venues move together
36
WORKING DRAFT
AMERICA TOGETHER
Featured conversation
Explore interest in a conversation with George W. Bush, Barack Obama and Ken Burns. Confirm roles, date options, requirements and costs.
Kitchen table speakers
Approach proposed participants including Margaret Hoover, Jamie Fly, Jane Harman and William McRaven through coordinated introductions.
Music headliners
Request availability and complete performance requirements for a small shortlist. Price talent, staging, sound, travel, security and recording rights.
Dallas venues
Test several date windows across the concert, conversations, art and dinner. Confirm capacity, security, catering, loading and any hold terms.
All participants remain proposed. Assign an outreach owner and track responses before making commitments.

## Slide 37
SEED FUNDING
The presenting sponsor can fund the start
37
WORKING DRAFT
AMERICA TOGETHER
Proposed lead position
Seek one $600,000 presenting sponsor. Explain the recognition, included benefits and the initial work that its contribution would enable.
Initial payment
Negotiate an agreed first payment for approved development and deposits. A pledge payable near the event does not provide early operating cash.
Defined use of funds
Agree on a seed budget, payment dates and permitted uses. Confirm the recipient of funds and who may authorize contracts and payments.
Music funding capacity
Three proposed $400,000 music positions total $1.2 million. This creates a funding goal for exceptional talent. Actual performance and production costs require quotes.

## Slide 38
PRODUCTION
A contracted producer establishes the costs
38
WORKING DRAFT
AMERICA TOGETHER
First assignment
Engage a producer for a defined development scope once authorized and funded. Obtain talent and venue estimates and a complete preliminary production budget.
Comparable proposals
Separate fees, deposits and final payments. Include catering, technical production, staffing, security, insurance and professional recording.
Cash requirements
Build a payment calendar. Separate cash sponsorship from donated support, and show when ticket receipts may become available for expenses.
Scope and oversight
Laura and Brad guide development. The producer coordinates specialists and vendors. Written scopes, fees and approval limits govern each commitment.

## Slide 39
NEXT DECISION
The first milestone before booking Dallas
39
WORKING DRAFT
AMERICA TOGETHER
Authority and interest
Written outreach permission and a clear Freedom House contact. Credible participant interest with roles and availability documented.
Dates and costs
Compatible date options and venue proposals, plus a preliminary budget supported by quotes. Identify essential participants and workable alternatives.
Committed cash
A presenting sponsor agreement with usable initial funding, a payment schedule and a defined cash threshold for the next commitments.
Decision to proceed
Review the package together. Confirm affordable scope and authorize specific contracts. Announce only approved dates, venues and confirmed participants.
March 1, 2027 remains a working target. Availability, funding and approvals determine the confirmed date.